## IASS
Instance Ambulance Service System Milestone ID | Proposed Milestone Date | Description | References
IASS#0 | 25-Feb-2019 (End of Sprint 1) | Familiar with system requirement (s/w and h/w) & setup. | https://developer.android.com/studio/install
IASS#1 | 30-Feb-2019 (End of Sprint 2) | Desinging of GUI using android studio | https://developer.android.com/studio/projects/templates
IASS#2 | 10-March-2019 (End of Sprint 3) | Collecting information related GPS and databse tables | https://youtu.be/Ak8uRvlpGS0
IASS#3 | 20-March-2019 (End of Sprint 4) | Coding part for Activity intent ,database connectivity and GPS coding | https://developer.android.com/training/basics/firstapp/starting-activity
IASS#4 | 30-March-2019 (End of Sprint 5) | Location tracking and connectivity, sending alert in the form of notification on Android phone | https://developer.android.com/training/location/receive-location-updates
IASS#5 | 10-April-2019 (End of Sprint 6) | Testing the apllication and Integreting all the GUI for deploying the application | https://developer.android.com/studio/test https://developer.android.com/studio/publish

## Comm
A git repo will be provided by Mini project Incharge where all the code should be checked in.
Bi-weekly meeting will be held for regular sync up and feedback. Days can be flexible, proposed is Monday and Friday
Choice of library / frameworks are flexible
Guide will provide necessary help during the completion of project
All the relevant formats & sheets are made available on MOODLE server.
Make the best use of Mini project Practical hours.
Continuously engage with guide.